## Sheet1
Task Name | Best Case | Most Likely | Worst Case | PERT
start project
Hosting
Location contract | 0.88 | 1 | 1.8 | 1.1133
Calculate budget | 0.25 | 0.3 | 0.35 | 0.3
Scheduling the party | 0.13 | 0.15 | 0.2 | 0.155
Getting permit | 0 | 0 | 0
Team plan | 0.04 | 0.1 | 0.3 | 0.12333
Design | 0.31 | 0.5 | 2 | 0.71833
Site preparation | 3.19 | 3.3 | 3.5 | 3.315
start preperation
Checking attendance | 0.44 | 0.6 | 0.8 | 0.60667
Create registration | 0.06 | 0.4 | 1 | 0.44333
Round up the list who will participate the party | 0.13 | 0.14 | 0.15 | 0.14
Drone obstacle | 0.38 | 0.5 | 0.6 | 0.49667
Obstacle design | 0.13 | 0.2 | 0.25 | 0.19667
Set up | 0.13 | 0.2 | 0.3 | 0.205
Clean up | 0.06 | 0.1 | 0.15 | 0.10167
Driver | 2.88 | 3 | 3.5 | 3.0633
transport everything to the party | 0.25 | 0.5 | 0.55 | 0.46667
load the items off | 0.13 | 0.15 | 0.17 | 0.15
load items back in | 0.13 | 0.15 | 0.17 | 0.15
drive back | 0.25 | 0.5 | 0.55 | 0.46667
Chef | 2.88 | 3 | 3.22 | 3.0167
get ingredients | 0.25 | 0.5 | 0.55 | 0.46667
drive to the event | 0.25 | 0.3 | 0.35 | 0.3
cook | 0.13 | 0.14 | 0.15 | 0.14
serve | 0.75 | 2 | 3 | 1.9583
clean up | 0.06 | 1.5 | 3 | 1.51
drive back | 0.25 | 0.5 | 0.55 | 0.46667
Pilot manager | 0.19 | 0.2 | 0.21 | 0.2
Set up chair and video frequency | 0.06 | 0.07 | 0.08 | 0.07
Clean up | 0.13 | 0.2 | 0.25 | 0.19667
Charger
Set up charging station | 0.06 | 0.08 | 0.1 | 0.08
Clean up | 0.06 | 0.08 | 0.1 | 0.08
DJ
create a playlist | 0.06 | 0.1 | 0.11 | 0.095
set up instruments, speakers | 0.13 | 0.2 | 0.25 | 0.19667
clean up | 0.25 | 0.3 | 0.4 | 0.30833
Soldering expert
set up soldering station and workbench | 0.03 | 0.04 | 0.05 | 0.04
clean up | 0.06 | 0.1 | 0.11 | 0.095
Simulator
set up computers and controllers | 0.06 | 0.1 | 0.2 | 0.11
clean up | 0.12 | 0.2 | 0.25 | 0.195
Builders
10 people set up the environment following the design like umbrella, trash can, chairs, walking path and so on | 0.3 | 0.5 | 0.6 | 0.48333
clean up | 0.3 | 0.5 | 0.6 | 0.48333
end site prep
media
start media
Poster design | 0.13 | 0.2 | 0.3 | 0.205
Filming | 0.25 | 0.26 | 0.27 | 0.26
Editing | 0.38 | 0.4 | 1 | 0.49667
Advertise | 0.5 | 0.55 | 0.6 | 0.55
end media
Foods (food truck)
Tacos | 0.13 | 0.14 | 0.15 | 0.14
Fajita | 0.13 | 0.14 | 0.15 | 0.14
Burritos | 0.13 | 0.14 | 0.15 | 0.14
Churros | 0.13 | 0.14 | 0.15 | 0.14
Horchata and drinks | 0.13 | 0.14 | 0.15 | 0.14
party start
Activities
Simulator | 1 | 1.2 | 1.3 | 1.1833
Drone racing | 1 | 1.2 | 1.3 | 1.1833
Drone freestyle | 1 | 1.2 | 1.3 | 1.1833
Drone workshop | 1 | 1.2 | 1.3 | 1.1833
Pilot meetup | 1 | 1.2 | 1.3 | 1.1833
Battery charge | 1 | 1.2 | 1.3 | 1.1833
end activites
Lodging
start hotel
Find local hotel | 0.06 | 0.1 | 0.25 | 0.11833
Collaboration | 0.25 | 0.26 | 0.27 | 0.26
Offering special deal | 0.13 | 0.14 | 0.145 | 0.13917
Attendance transportation | 0.13 | 0.14 | 0.15 | 0.14
finish project